## Sheet1
Task Name | Duration | Contributor | Start | Finish | Role
TickTake App | 23 | Everyone | 2023-12-30 | 2024-01-22
Project Management:
Requiments gathering | 2 | Syed Kaif Ali | 2023-12-30 | 2024-01-01 | Project Manager
Business Analyst:
Work flow of app | 3 | Tashfeen | 2024-01-01 | 2024-01-04 | Business Analyst
Competitor Analysis | 3 | Tashfeen | 2024-01-01 | 2024-01-04 | Business Analyst
TickTake App Analysis | 3 | Tashfeen | 2024-01-01 | 2024-01-04 | Business Analyst
UI Design:
Create UI design on figma | 5 | Taha Mir | 2024-01-01 | 2024-01-06 | UI Designer
DataBase Schema:
Design database schema | 2 | Hamid | 2024-01-01 | 2024-01-03 | Back-end
App UI/Logic implementation:
Event Manager Front-end:
Event Creation | 5 | Abdul Majid | 2024-01-09 | 2024-01-14 | App Front-end
Account creation | 5 | Abdul Majid | 2024-01-09 | 2024-01-14 | App Front-end
Log in | 5 | Abdul Majid | 2024-01-09 | 2024-01-14 | App Front-end
Log out | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
Approve tickets | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
Cancel tickets | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
Remove events | 5 | Ahmad Irfan | 2024-01-09 | 2024-01-14 | App Front-end
User Front-end:
Open events
Open events
View upcoming events
View past events
View favorite events
Remove events from favorites
Buy ticket for an event
Generate QR code
Sort events
View events by categories
Formulas:
Duration = DATEDIF([Start], [Finish], "d")